## 54e - SAMPLE COST REPORT1
"MYSTERY IN DINGLEY DELL" - Cost Report Summary for the period ended 26/5/06
|  | SPENT THIS PERIOD | SPENT TO DATE | ESTIMATE TO COMPLETE | ESTIMATED FINAL COST | BUDGET | TOTAL OVER/UNDER | OVER/UNDER THIS PERIOD
ABOVE THE LINE COSTS
A.1 | STORY & SCRIPT |  | 50000 |  | 50000 | 50000 | 0 | 0
A.2 | DEVELOPMENT |  | 27563 |  | 27563 | 27563 | 0 | 0
B.1 | PRODUCERS |  | 40000 | 7000 | 47000 | 47000 | 0 | 0
B.2 | DIRECTORS |  | 40000 | 7000 | 47000 | 47000 | 0 | 0
E(a) | CAST - PRINCIPALS |  | 0 |  | 0 | 0 | 0 | 0
| TOTAL ABOVE THE LINE COSTS | 0 | 157563 | 14000 | 171563 | 171563 | 0 | 0
PRODUCTION COSTS
C | UNIT FEES & SALARIES
1 | PRODUCTION MGMT |  | 48122 |  | 48122 | 46000 | 2122 | 0
2 | PRODUCTION ACCOUNTANCY | 500 | 20000 | 1000 | 21000 | 21000 | 0 | 0
3 | A Ds & CONTINUITY |  | 28973 |  | 28973 | 28000 | 973 | 0
4 | CAMERA CREW |  | 25600 |  | 25600 | 23500 | 2100 | 0
5 | SOUND CREW |  | 11200 |  | 11200 | 11000 | 200 | 0
6 | LIGHTING CREW |  | 17300 |  | 17300 | 16200 | 1100 | 0
7 | GRIPS CREW |  | 12640 |  | 12640 | 11100 | 1540 | 0
8 | COSTUME CREW |  | 27360 |  | 27360 | 24000 | 3360 | 0
9 | MAKE-UP CREW |  | 9600 |  | 9600 | 9850 | -250 | 0
10 | HAIRDRESSING CREW |  | 6100 |  | 6100 | 5500 | 600 | 0
11 | ART DEPARTMENT |  | 51987 |  | 51987 | 49450 | 2537 | 0
12 | ACTION VEHICLES CREW |  | 0 |  | 0 | 0 | 0 | 0
13 | LIVESTOCK CREW |  | 0 |  | 0 | 0 | 0 | 0
14 | CONSTRUCTION DEPT |  | 7500 |  | 7500 | 8000 | -500 | 0
15 | SPECIAL EFFECTS & ARMOURY |  | 0 |  | 0 | 0 | 0 | 0
16 | VISUAL EFFECTS & ANIMATION |  | 0 |  | 0 | 0 | 0 | 0
17 | OHS & SAFETY CREW |  | 750 |  | 750 | 750 | 0 | 0
18 | TUITION &TECHNICAL ADVISERS |  | 3640 |  | 3640 | 4600 | -960 | 0
19 | SECOND UNIT CREW |  | 0 |  | 0 |  | 0 | 0
20 | OVERSEAS UNIT/ CREW |  | 0 |  | 0 |  | 0 | 0
24 | OVERTIME &LOADINGS |  | 20566 | 500 | 21066 | 30000 | -8934 | 0
| UNIT FEES & SALS. SUB-TOTAL | 2700 | 334434 | 3500 | 337934 | 330850 | 7084 | 1300
D | FRINGES AND WORKERS COMP | 956 | 19651 | 4526 | 24177 | 28160 | -3983 | 109
"MYSTERY IN DINGLEY DELL" - Cost Report Summary for the period ended 26/5/06
|  | SPENT THIS PERIOD | SPENT TO DATE | ESTIMATE TO COMPLETE | ESTIMATED FINAL COST | BUDGET | TOTAL OVER/UNDER | OVER/UNDER THIS PERIOD
E(b) | CASTING & CAST |  | 0 |  | 0 |  | 0 | 0
1 | CASTING |  | 10156 |  | 10156 | 10000 | 156 | 0
2 | PRINCIPALS |  | 56612 | 2000 | 58612 | 55600 | 3012 | 0
3 | SUPPORTS |  | 16559 |  | 16559 | 23000 | -6441 | 0
4 | STANDINS & DOUBLES |  | 0 |  | 0 |  | 0 | 0
5 | STUNTS |  | 2500 |  | 2500 | 2000 | 500 | 0
6 | EXTRAS |  | 4222 |  | 4222 | 4000 | 222 | 0
F.1 | COSTUMES |  | 9506 |  | 9506 | 8500 | 1006 | 0
F.2 | MAKEUP AND HAIRDRESSING |  | 4000 |  | 4000 | 4000 | 0 | 0
G.1 | LOCATIONS |  | 32560 |  | 32560 | 25000 | 7560 | 0
G.2 | STAGE RENTAL |  | 4885 |  | 4885 | 4500 | 385 | 0
H | SETS & PROPERTIES
H.1 | CONSTRUCTION |  | 10632 |  | 10632 | 6500 | 4132 | 0
H.2 | PROPS &SETDRESSING |  | 22678 |  | 22678 | 24000 | -1322 | 0
H.3 | ACTION PROPS/ VEHICLES |  | 5432 |  | 5432 | 2000 | 3432 | 0
H.4 | LIVESTOCK |  | 250 |  | 250 | 0 | 250 | 0
H.5 | SPECIAL EFFECTS & ARMOURY |  | 0 |  | 0 | 0 | 0 | 0
H.6 | VISUAL EFFECTS |  | 0 |  | 0 | 0 | 0 | 0
H.7 | ANIMATION & PUPPETRY |  | 0 |  | 0 | 0 | 0 | 0
I | IMAGE & SOUND CAPTURE |  | 35414 | 200 | 35614 | 30200 | 5414 | 0
J | INSERTS, STOCK & ARCHIVAL |  | 0 |  | 0 | 0 | 0 | 0
K | EQUIPMENT & STORES
K.1 | CAMERA |  | 20544 |  | 20544 | 21000 | -456 | 0
K.2 | SOUND EQUIP &STORES |  | 5400 | 0 | 5400 | 5100 | 300 | 0
K.3 | LIGHTING EQUIP & STORES |  | 27691 |  | 27691 | 25700 | 1991 | 0
K.4 | GRIPS EQUIP &STORES |  | 11600 |  | 11600 | 11000 | 600 | 0
K.5 | UNIT EQUIP &STORES |  | 6393 | 0 | 6393 | 6000 | 393 | 0
L | RENTALS,STORAGE&EDITING | 150 | 38040 | 1500 | 39540 | 36900 | 2640 | 290
M | TRAVEL &TRANSPORT | 30 | 38124 | 2500 | 40624 | 32400 | 8224 | 800
N | ACCOMM ,LIVING,CATERING | 56 | 24169 | 1262 | 25431 | 25000 | 431 | 650
O | INSURANCES | 800 | 18312 | 7500 | 25812 | 23461 | 2351 | 0
P | OFFICE EXPENSES | 2577 | 26124 | 2000 | 28124 | 21963 | 6161 | 1000
Q | OFFSHORE SHOOT |  | 0 |  | 0 | 0 | 0 | 0
"MYSTERY IN DINGLEY DELL" - Cost Report Summary for the period ended 26/5/06
|  | SPENT THIS PERIOD | SPENT TO DATE | ESTIMATE TO COMPLETE | ESTIMATED FINAL COST | BUDGET | TOTAL OVER/UNDER | OVER/UNDER THIS PERIOD
POSTPRODUCTION COSTS
R | POSTPRODUCTION CREW | 2200 | 28740 | 2000 | 30740 | 28000 | 2740 | 1300
S | POST RENTALS & OFFICE EXPENSES |  | 3366 | 2000 | 5366 | 3000 | 2366 | -200
T | POST TRAVEL & ACCOMMODATION | 0 |  | 0 | 0 | 0 | 0 | 0
U | IMAGE POSTPRODUCTIN | 1560 | 1560 | 75463 | 77023 | 68500 | 8523 | 3845
V | SOUND POSTPRODUCTION |  | 0 | 75600 | 75600 | 73465 | 2135 | 0
W | MUSIC | 3500 | 7000 | 23000 | 30000 | 25000 | 5000 | 5000
X1 | PUBLICITY |  | 5700 |  | 5700 | 5400 | 300 | 0
| STILLS |  | 4756 | 2500 | 7256 | 2560 | 4696 | 0
X2 | DELIVERY REQUIREMENTS
| TOTAL BELOW THE LINE | 12329 | 793914 | 203551 | 997465 | 930859 | 66606 | 12794
INDIRECT COSTS
Y | BUSINESS &LEGAL | 1000 | 8256 | 2643 | 10899 | 10000 | 899 | 0
Z | OVERHEADS |  | 0 |  | 0 | 0 | 0 | 0
| TOTAL INDIRECT COSTS | 1000 | 8256 | 2643 | 10899 | 10000 | 899 | 0
| TOTAL ALL CATEGORIES | 13329 | 959733 | 220194 | 1179927 | 1112422 | 67505 | 12794
| COMPLETION GUARANTEE |  | 30000 |  | 30000 | 30000 | 0 | 0
| CONTINGENCY |  | 0 |  | 0 | 97578 | -97578 | 0
| FINANCE |  | 0 | 30000 | 30000 | 30000 | 0 | 0
| MARKETING |  | 0 |  | 0 |  | 0 | 0
| PRODUCTION LEVIES |  | 0 |  | 0 |  | 0 | 0
| T O T A L | 13329 | 989733 | 250194 | 1239927 | 1270000 | -30073 | 12794