## A
|  | Project Name: | SAMPLE
SUBJECT TO AMENDMENT AS REQUIRED
Week |  |  | Cost | $ | FFC | $ |  | $
Commencing |  | Schedule | Report | FFC | % | Broadcaster | % | Total
Monday | No. |  |  | 215150 |  | 115850 |  | 331000
|  |  |  | 64545 | 30% | 28963 | 25% | 93508
2005-12-05 | 5 | Pre
2005-12-12 |  | Pre
2005-12-19 |  | Pre
2005-12-26 |  | Pre
2006-01-02 |  | Pre
Pre
Pre
2006-01-09 | 3 | Shoot | 2006-01-09 | 64545 | 30% | 28963 | 25% | 93508
2006-01-16 |  | Shoot
2006-01-23 |  | Shoot
2006-01-30 |  | Shoot
| 12 | Post | 2006-02-06 | 64545 | 30% |  |  | 64545
2006-02-06 |  | Post
2006-02-13 |  | Post
2006-02-20 |  | Post
2006-04-02 |  | Rough Cut / FFC Screening | 2006-04-02 | 5378.75 | 2.5% | 28963 | 25% | 34341.75
Post
Post
Post
2006-04-17 |  | Only after viewing fine cut | 2006-04-17 | 5378.75 | 2.5% |  |  | 5378.75
2006-04-24 |  | Sound Post
2006-05-01 |  | Sound Post
2006-06-06 |  | Delivery and executed sales agreement | 2006-06-06 | 4757 | 2.211% | 28961 | 25% | 33718
2006-07-06 |  | Final Cost Report and Audit | Final | 6000 | 2.789% |  |  | 6000
|  | TOTAL |  | 215149.5 | 100% | 115850 | 100% | 330999.5
1. Percentages are a guide and may vary slightly due to the individual producers needs.
2. Note 2003/04 Final audit payments is $6,000 for accords and $10,000 for non-accords
Formulas:
Commencing = [Commencing, row above]+7
Report = [Commencing]
Report = +[Commencing]