## Sheet1
PRELIMINARY PRE-PRODUCTION SCHEDULE - "CHAT"
A blank of this form can be found on www.afc.gov.au |  |  |  | As at | 2006-05-18
WK | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
5 | 2006-07-24 | 2006-07-25 | 2006-07-26 | 2006-07-27 | 2006-07-28
| Production & Costume | 0900-1600: director to | 083 - Insurance Mtg | AM: Location recces: | Meetings:
| Designers, 1st AD start | meet with DOP, Prod | 1000- PROD MEETING | Director, 1st AD, Prod | DOP and Prod Mgr
|  | & Costume designers | Diretor, designer, PM, | Designer, DOP, Loc | DOP and Designer
| DOP starts for 1 week | for briefing on script | loc mgr, DOP, producer, | Manager | DOP and Director
| meet director & designers |  | editor, writer, costume
designer
| PM: Meeting director, | PM: Budget meetings
| DOP and location mgr | with HODs & Prod Mgr | PM: Director in casting
4 | 2006-07-31 | 2006-08-01 | 2006-08-02 | 2006-08-03 | 2006-08-04
| Accounts starts | 0800: Location Recces | 0800: OHS Meeting | 0800-1000: SPFX and | 0800-1200: Art Dept
| 0800-1000: PROD MTG | Director, 1st AD, Prod | All HODs | stunts meeting | & Costume Meetings
| All HODs | Designer, Loc Mgr |  |  | wth director
| Others as available |  | 1030-1100: Director & | 1000-1200: DVFX
|  |  | producer interview | Meeting
| 1100-1700 |  | stills photographers
| Producer & director |  |  | PM: Director in casting | PM: Director in casting
in casting
3 | 2006-08-07 | 2006-08-08 | 2006-08-09 | 2006-08-10 | 2006-08-11
| 0800-1000: PROD MTG | 0800: Costume fittings | 0800-1000: Loc recces | 0800-1000: Loc recces | 0800-1000: Loc recces
| All HODs | and makeup meetings | Director, 1st AD, Prod | Director, 1st AD, Prod | Director, 1st AD, Prod
| Others as available | with cast begin | Designer, Loc Mgr | Designer, Loc Mgr | Designer, Loc Mgr
|  | 1000: REHEARSALS | 1000: REHEARSALS | 1000: REHEARSALS | 1000: REHEARSALS
1200: Director briefs
Makeup & Hairdressing
2 | 2006-08-14 | 2006-08-15 | 2006-08-16 | 2006-08-17 | 2006-08-18
| DOP resumes | 0800-1000: Postproduction | 0800-1000: Stills Shoot | 0800 - Shoot special | 0800: View camera tests
| 0800-1000: PROD MTG | Meeting - director, producer, | Principal cast, crew as | camera tests, jewellery | at laboratory
| including OHS briefing | all relevant crew, all facilities | required, director
| All HODs | 1000: REHEARSALS | 1000: REHEARSALS | 1000: REHEARSALS | 1000: REHEARSALS
Others as available
1000: Location recces
Director, 1st AD, Prod
Designer, Loc Mgr, DOP
1 | 2006-08-21 | 2006-08-22 | 2006-08-23 | 2006-08-24 | 2006-08-25
| Camera check & tests | 0800: Camera tests for | 0800-1000:
| start | principal cast with makeup | FINAL PROD MTG | 1000: REHEARSALS | 1000: REHEARSALS
| 0800-1800 | and costume | All HODs
| TECHNICAL RECCE |  | Others as available
| Director, all HODs, other |  | 1000: View camera
| crew as relevant |  | tests at telecine house | Issue first day callsheet
|  |  | 1200: REHEARSALS | and all paperwork
Pre-shoot drinks